Parish Council Revised Action Plan 2023 – 2024

Approved by Full Council on:    6Th June 2023                                                                                                                  Minute Reference: 23/24.X

Waltham Parish Council’s Action Plan identifies what the Council aims to achieve over the next year with reference to the annual budget. The plan will be reviewed  in-year with items added or deleted according to priorities identified in the Parish Plan or as circumstances change.

| Aim | Objectives | Responsibility | Budget | Action |
| --- | --- | --- | --- | --- |
| Ensure that all Governance and Accountability requirements are met. | Publish agendas, minutes, meetings and calendar on the website. | Clerk. | Within salary budget. | Monthly |
| Maintain budgetary control. Ensure transparency of information regarding Council Finances. | Publish information regarding payments, budget, audit, and annual return. | RFO with support of Cllr Robinson | Within salary budget. | Monthly summary & quarterly review |
| Publish information on Councillor Responsibilities. | Consult with Councillors on range of activities and preferences. | Clerk in consultation with Councillors. | Within Salary budget. | Councillor updates at Full Council meetings |
| Ensure that all Policies and Procedures are regularly reviewed. | Maintain and publish Policy and Procedures section on Website. | Clerk with resolutions by full Council. | Within salary budget. | Annual Review according to need |
| Preparations for the development of a Parish Plan | A process for Parish Council and the local Community to work together to protect and improve the social, recreational, and environmental well-being of and the lives of all who live, visit and work here. | Clerk with support from Councillors | £500 approved budget | *Launch questionnaire April. *Quantitative & qualitative analysis June/July *Updates on Facebook, PAWNews and Parish Council minutes. *Full report to Council/Parishioners in September. |
| Collaborate with neighbouring parishes on areas of mutual interest | Explore potential for joint work with Chartham PC on public rights of way | Cllr John Barry & Clerk. | Within salary budget. | As part of Parish Plan development |
| Continuation of Improved road safety initiatives in the Parish. | Review potential hazards and options for improvement. including gate sign. | Cllr John Barry and Clerk in collaboration with KCC | Indicative budget of £2,500 plus £762 Capital Grant for gate sign | Parishioner consultation on options Liaise with KCC on purchase/installati0n. |
| Seek a Foundation Award under the Local Council Award Scheme. | Demonstrate that documentation is in place to meet the Criteria. | Clerk in consultation with Councillors leading to Resolution. | £120 from General Reserves | Progress reports at Council Meetings and APM |

WPC/asm/26:05:2023