Waltham Parish Council

EST. 1894

Waltham Parish Plan - Proposed Action Plan

In his report to the 2022 Annual Parish Meeting the Chairman of Waltham Parish Council indicated an intention to start developing the foundations for a 'Parish Plan'.

£1,000 has been identified in the 2022 – 23 Budget.

This outline Action Plan takes the intention further by highlighting ten key stages of development, identified as best practice by the Countryside Agency (2004)

- Introduction - An opportunity for parishioners to shape their future

- What is a Parish Plan? Setting out a vision of how the community wants to develop and

what needs to be done to achieve it.

- Why produce a Parish Plan? Increased individual participation and increased opportunities to gain support to enhance the parish’s economic, social, and environmental wellbeing.

- Who should be involved?  everyone who lives or works or plays a part in the community; everyone who has an impact on what goes on in the community; everyone you hope to influence.

- Preparing the ground: Get the community on board; Find someone to help you; Set up a steering committee and agree a working protocol.

- Developing the scope of the plan:  Choose subject areas; Review existing appraisals, surveys, and plans; Identify special designations such as AONBs, SSSIs etc; Sound out the community; Draw up a plan brief.

- Getting down to business – collecting information: Get the views of everyone possible;

Research District and County plans and Policies; Investigate best practice in other areas;

Consider use of an online mapping tool.

- Writing up and discussing your findings:  Produce a draft report; discuss the findings with all

Involved.

- Producing the action plan:  Decide what action is needed; Prioritise; Submit plan to parish

council; Design & print; Distribute to community & partners.

- Implementation, monitoring, and review: Parish council adopts the plan as policy.

Encourages local authorities and others to work on their action points; Ongoing steering committee or parish council allocates tasks to working groups; Open dialogue with partners and funders; Publicise and celebrate successes; Monitor and review progress.

It is expected that the Action Plan will take approximately one year to complete.

WPC/asm/27:06:2022