Waltham Parish Council

EST. 1894

2022 Annual Governance and Accountability Review Timetable

Introduction.

This timetable summarises the action needed to meet the External Auditors requirements for a review of Councils 2021/22 Accounts and the statutory period for the Exercise of Public Rights.

| Date | Action | Completed |
| --- | --- | --- |
| 05:04:22 | Full Budget report to Council. Formal approval of Accounts | 05:04:22 Minute 22/23.05 |
|  | Finance Pack to Internal Auditor | 11:04:22 |
|  | Receipt of Annual Internal Audit Report | 01:05:22 |
| 26:04:22 | Summary report to Annual Parish Meeting |  |
|  | Preparation of Part II AGAR forms | 26:04:22 |
| 03:05:22 | Formal Approval of AGAR : Decision to submit Certificate of Exemption (deadline 30:06:22)) : Confirmation of Internal Control Objectives : Confirmation of Annual Governance Statement : Certification of Accounting Statement 2021/22 : Approval of Analysis of Variances and Bank Reconciliation : Publication of the AGAR Return, the period for the Exercise of Public Rights and Certification of exemption (before 01:07:22) | Final version Submitted 19:05:22 √ √ √ √ 06:06:22 |
| 13:06:22 | Beginning of Statutory Period for the Exercise of Public Rights |  |
| 22:07:22 | End of Statutory Period. |  |
| 06:09:22 | Formal report to Council on outcome |  |

Timetable approved by Council on the 5th of April 2022 Minute Reference: 22/23.05